## BUILD SEQUENCE
SKM STUDIO MAPS — BUILD SEQUENCE ¦ 50 Steps in Exact Order ¦ Never Skip a Step
Steps 1-10 RED = Foundation FIRST ¦ 11-20 ORANGE = Core ¦ 21-35 AMBER = Features ¦ 36-50 GREEN = Advanced
HOLI CHALLENGE: Mar 3-14, 2026 ¦ 11 days ¦ Target minimum 5 steps per day to ship on time
Change STATUS to Done when step complete — Update Sheet 1 Tracker manually
Step | What to Build | Phase | Why This Order — What It Unlocks | Test to Confirm It Works | Est Hours | Maplify Ref | STATUS
1 | database/schema.sql — ALL CREATE TABLE statements | P0 | Zero features work without database tables. This is the foundation of everything. | Run: SELECT * FROM users LIMIT 1 — table exists even if empty. No error. | 3h | — | Todo
2 | Next.js 15 project setup + install all packages | P0 | Need the base project before writing any code. Install openpyxl, neon, razorpay, leaflet, next-pwa etc. | Run: npm run dev — localhost:3000 loads without errors. | 1h | — | Todo
3 | lib/db.ts — Neon serverless client | P0 | Every single API route imports this file. Build perfectly once. | Create test route GET /api/test — returns table count from Neon. No error. | 0.5h | — | Todo
4 | app/globals.css — Full CSS design system | P0 | Every component uses CSS variables and classes from here. Build before any UI. | Add className btn-primary to a test button — renders gold with hover effect. | 4h | Amber not teal | Todo
5 | types/database.ts + types/api.ts | P0 | TypeScript types prevent silent runtime crashes. Must define before building components. | No red TypeScript errors when importing Business or User type in any file. | 2h | — | Todo
6 | components/ui/ — All base components | P0 | Used 100+ times across the platform. Build once perfectly. Never rebuild. | Import Button Card Modal Toast Badge in a test page — all render correctly. | 6h | Clean Maplify card style | Todo
7 | lib/auth/session.ts — requireAuth guard | P0 | Security guard for all 5 dashboards. Must exist before building any protected route. | Call requireAuth with no cookie set — throws 401 response. Correct behavior. | 1h | — | Todo
8 | Magic Link Auth — complete login flow | P1 | Without working auth nobody can reach any dashboard to test anything. | Full flow: go to /login, enter email, check inbox, click link, land on correct dashboard. | 4h | Image 6 match exactly | Todo
9 | Dashboard layout shell — sidebar and topbar | P0 | All 5 dashboards inherit this single wrapper. Build once perfectly. | Log in as any role — sidebar shows correct role-specific menu items. | 3h | Image 2 sidebar nav | Todo
10 | Public layout shell — header and footer | P0 | All public pages inherit this. Legal links in footer required by IT Act. | Go to localhost:3000 — header with logo and footer with legal links both visible. | 2h | Image 1 header style | Todo
11 | DashboardTable generic component | P0 | 30+ tables across all dashboards depend on this. Build perfectly once. | Pass dummy data array — search works, pagination works, export Excel works. | 4h | Image 4 clean table | Todo
12 | Super Admin overview + stats API | P2 | Need admin access to manage and test everything else you build. | Log in as super_admin — 4 stat cards show with real numbers from DB. | 3h | Image 2+5 exact layout | Todo
13 | Super Admin Feature Flags tab | P2 | Need to toggle features on/off without code deploy during development. | Toggle any flag — query DB immediately — value changed. No redeploy needed. | 2h | — | Todo
14 | Super Admin Users and RBAC | P2 | Need to manage and change user roles before role-specific dashboards work. | View your own user record with super_admin role badge correctly shown. | 3h | — | Todo
15 | Icon and Template Library in Super Admin | P2 | Must pre-load templates before owner AI tools have any content to show. | Add Restaurant description template — go to Owner AI tools — template appears. | 4h | — | Todo
16 | Listing Submit 7-Step Form | P4 | Platform needs real content before anything else can be properly tested. | Submit a test listing — check Neon DB — row appears with status pending. | 8h | — | Todo
17 | Super Admin Listings Queue — Approve | P2 | Need to approve the test listing from step 16 to test all public pages. | Click Approve on test listing — status changes to approved — public pages show it. | 4h | Image 4 clean and simple | Todo
18 | Homepage — public landing page | P7 | First page every user sees. Must look real and complete with real data. | Go to localhost:3000 — hero, category grid, city pills all show with real data. | 4h | Image 1 search bar | Todo
19 | Business Profile Page /b/[slug] | P7 | Most important public page. Every listing link leads here. | Go to /b/your-test-listing — all fields display: name, hours, photos, map. | 8h | Contact buttons at top | Todo
20 | Owner dashboard — Listings Overview page | P4 | Owners need to see their listing status and manage from their dashboard. | Log in as owner — listing card shows with status badge and quick stats. | 4h | — | Todo
21 | Razorpay Integration — TEST MODE ONLY | P10 | Revenue engine. Test thoroughly before showing to real users. | Use test card 4111 1111 1111 1111 — subscription activates in DB. Invoice generated. | 5h | — | Todo
22 | Search Results Page — split layout | P7 | Primary organic traffic page. Most users enter here from Google. | Search restaurants in Mumbai — cards on left, Leaflet map on right. Filters work. | 5h | Image 1 EXACT split | Todo
23 | Owner Analytics Tab | P4 | Core value proposition of Featured plan. Must show real data. | Log in as Featured owner — line graph shows daily views and calls last 7 days. | 4h | — | Todo
24 | Notification System — all 3 channels | P9 | User feedback loop. Without this platform feels broken and unresponsive. | Approve listing — owner sees bell notification within 30 seconds. Email arrives. | 5h | — | Todo
25 | Points Gamification Engine | P5 | Community growth system. Core contributor motivation. | Approve a listing — check user_points table — submitter has plus 50 points. | 5h | — | Todo
26 | Moderator Dashboard | P3 | Scale beyond super admin manually approving every listing. | Log in as moderator — pending queue shows — approve one listing successfully. | 5h | Image 4 simple queue | Todo
27 | Leaflet Maps — Business and City maps | P10 | Maps increase trust and power the contributor exploration mode. | Business profile page — map shows correct pin location. ssr:false working. | 3h | — | Todo
28 | Programmatic SEO City and Category pages | P8 | Primary Google organic traffic source. Start indexing as early as possible. | Go to /city/mumbai/restaurants — listings show, FAQ shows, schema markup present. | 4h | — | Todo
29 | OG Image Generation at /api/og | P8 | Social sharing cards for WhatsApp. Every listing share looks professional. | Share any listing link on WhatsApp — gold and dark preview card appears. | 2h | — | Todo
30 | InternalLinks block + Sitemap + robots.txt | P8 | SEO link equity between pages. Google discoverability from day 1. | View source on homepage — InternalLinks section before footer. Sitemap loads. | 3h | JustDial style | Todo
31 | Profile Contributor Dashboard | P5 | Contributors need visibility into their progress to stay motivated. | Log in as profile role — see points balance, streak, level, multiplier breakdown. | 4h | — | Todo
32 | Floating Support Bot | P9 | IT Act Section 79 compliance. Legal requirement for platform. | Click Help button — report bug — ticket created — confirmation email received. | 4h | — | Todo
33 | Listing Edit Form — owner can edit | P4 | Owners need to keep their listing information updated. | Edit phone number — save — check public profile — updated within 60 seconds. | 3h | — | Todo
34 | Owner AI Tools — template based zero cost | P4 | Key value prop for MSME owners with no time to write content. | Click Description Writer — choose Restaurant template — text fills description field. | 2h | — | Todo
35 | Owner Leads Export Excel | P4 | Core MSME value prop. Owners see ROI in familiar Excel format. | Click Download Excel — file opens in Excel with leads data and rupee symbols. | 3h | MSME loves Excel | Todo
36 | Map Exploration Mode — contributor | P5 | Core contributor engagement loop. How contributors earn points daily. | Open explore map — click red unverified pin — verify fields — points awarded. | 6h | — | Todo
37 | Public Leaderboard | P5 | Social competition drives long-term contributor retention. | Go to /leaderboard — rankings show with city and national scope filters. | 3h | — | Todo
38 | Professional Profile /pro/[slug] | P7 | Opens up 200 million informal worker market in India. | Create test professional profile — go to /pro/test-name — page renders fully. | 5h | — | Todo
39 | Near Me GPS Page | P7 | Mobile-first GPS discovery. High intent users finding businesses nearby. | Open on mobile — allow GPS — listings within 5km show sorted by distance. | 2h | — | Todo
40 | DigiPin and Pincode SEO Pages | P8 | 3.5 crore unique SEO pages. Long-term organic search moat. | Test with 5 rows imported — go to /digipin/4FJ9MK — page renders with map. | 4h | — | Todo
41 | Location Quiz Mode — contributor | P5 | Depth of engagement. Keeps contributors active between exploration sessions. | Start quiz — 5 questions appear with timer — answer — points awarded correctly. | 5h | — | Todo
42 | Review Request Automation Cron | P9 | Hands-free review collection for Featured owners. Major time saver. | Trigger cron manually — check AiSensy dashboard — WhatsApp message sent. | 2h | — | Todo
43 | Claim Listing System | P9 | Business owners need to claim listings contributors submitted. | Click Claim button — fill form — moderator queue shows claim — approve it. | 3h | — | Todo
44 | Owner Competitor Intel Tab | P4 | Justifies Premium upgrade. Owners can benchmark against competitors. | Select competitor — comparison table shows green ahead and red behind colors. | 3h | — | Todo
45 | Owner Team Members Tab | P4 | Multi-staff businesses need to delegate listing management. | Invite staff via magic link — staff logs in — sees limited dashboard only. | 4h | — | Todo
46 | Bulk CSV Import for Owners | P9 | Chain businesses with multiple locations need batch import. | Upload sample CSV with 5 rows — preview table shows — submit — all 5 pending. | 2h | — | Todo
47 | PWA Setup — Add to Home Screen | P10 | Mobile app experience without App Store. Huge for MSME mobile users. | Open on Android Chrome — three dots menu shows Add to Home Screen option. | 1h | Web-to-app! | Todo
48 | Referral Program — Level 3 unlock | P5 | Viral growth loop. Contributors bring more contributors. | Reach Level 3 — Referrals tab unlocks — share link — signup tracked correctly. | 3h | — | Todo
49 | DigiPin Full National Import overnight | P13 | 3.5 crore SEO pages activated in one overnight run. | SELECT COUNT(*) FROM digipin_locations — shows crore scale row count. | Overnight | — | Todo
50 | GHL Integration — only 4+ SEO clients | P11 | Agency revenue multiplier. Only build when GHL monthly cost is justified. | Owner social tab shows scheduled posts from GHL calendar correctly. | 8h | — | Todo